## 17-239
Task Name | Estimate time( hour) | Take by | Actual Time | Status | Date Doing | Complete Process
Home (product listing) screen | 3 | Trần Khả Gia | 3 | Done |  | 3
Product details screen | 2 | Trần Khả Gia | 3 | Done |  | 2
Paging | 0.5 | Trần Khả Gia | 1 | Done |  | 0.5
User: Search product feature using ajax | 3 | Trần Khả Gia | 3 | Done |  | 3
Login with system's account | 4 | Trần Khả Gia | 4 | Done |  | 4
Logout | 0.2 | Trần Khả Gia | 1 | Done |  | 0.2
Authorization admin & user | 5 | Trần Khả Gia | 5 | Done |  | 5
User's edit profile screen | 5 | Trần Khả Gia | 5 | Done |  | 5
Admin's product management screen | 20 | Trần Khả Gia | 20 | Done |  | 20
Admin's account management screen | 12 | Trần Khả Gia | 12 | Done |  | 12
Notifying error by email | 0.5 | Trần Khả Gia | 1 | Done |  | 0.5
Total | 54.7 |  | 94.31% |  | Done task: | 100%
Requirement analyze | 9 | Đặng Hoàng Sơn | 9 | Done |  | 9
Learning MVC5, Entity Framework | 24 | Đặng Hoàng Sơn | 24 | Done |  | 24
[UI Mockup Mobile] Login/Register Screen | 2 | Đặng Hoàng Sơn | 2 | Done |  | 2
[UI Mockup Mobile] Home (Item Listing) Screen | 3 | Đặng Hoàng Sơn | 3 | Done |  | 3
[UI Mockup Mobile] Details Product Screen | 3 | Đặng Hoàng Sơn | 3 | Done |  | 3
[UI Mockup Mobile] Cart Screen | 4 | Đặng Hoàng Sơn | 4 | Done |  | 4
[UI Mockup Mobile] Checkout Screen | 2 | Đặng Hoàng Sơn | 2 | Done |  | 2
[UI Mockup Mobile] Notification screen | 2 | Đặng Hoàng Sơn | 2 | Done |  | 2
[UI Mockup Mobile] Admin's user management screen | 5 | Đặng Hoàng Sơn | 5 | Done |  | 5
[UI Mockup Mobile] Admin's category management screen | 2 | Đặng Hoàng Sơn | 2 | Done |  | 2
[UI Mockup Mobile] Admin's Report screen | 3 | Đặng Hoàng Sơn | 3 | Done |  | 3
[Implement UI] Login/Register Screen | 2 | Đặng Hoàng Sơn | 2 | Done |  | 2
[Implement UI] Home (Item Listing) Screen | 4 | Đặng Hoàng Sơn | 4 | Done |  | 4
[Implement UI] Cart Screen | 4 | Đặng Hoàng Sơn | 4 | Done |  | 4
Shopping cart | 10 | Đặng Hoàng Sơn | 10 | Done |  | 10
Login by facebook account | 4 | Đặng Hoàng Sơn | 4 | Done |  | 4
Login by google account | 1 | Đặng Hoàng Sơn | 1 | Done |  | 1
Integration Messenger Facebook | 2 | Đặng Hoàng Sơn | 2 | Done |  | 2
Integration PayPal | 14 | Đặng Hoàng Sơn | 14 | Done |  | 14
Deploy database to Azure SQL Database | 3 | Đặng Hoàng Sơn | 3 | Done |  | 3
Deploy web to Azure Web Service | 3 | Đặng Hoàng Sơn | 3 | Done |  | 3
Draw graph Dashboard Admin | 5 | Đặng Hoàng Sơn | 5 | Done |  | 5
Total | 78 |  | 159.2% |  | Done task: | 100%